## Sheet1
[6 empty] | Engineers (WLA) | Contractor (Kijima) | Client (Sasol)
WBS | Deliverable | Start date | End Date | Duration (Days) | Predecessors | Resource(s) |  |  | Progress | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19
1 | Units 066, 067 and 069 Demineralized Water |  |  |  |  | Engineers(WLA) | Contractor (Kijima) | Client (Sasol) |  | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun | Mon | Tues | Wednes | Thurs | Fri | Sat | Sun
1.1 | Concrete
1,1,1 | Break out defective concrete to spoil
1,1,1,1 | Spall depths not exceeding 25mm and not exceeding 50mm deep | 2023-10-27 | 2023-10-27 | 1 | 0 |  | x |  | 0%
1,1,1,2 | Spall depths exceeding 50mm | 2023-10-27 | 2023-10-27 | 1 | 0 |  | x |  | 0%
1,1,1,2,1 | Inspect and Sign off QCP | 2023-10-27 | 2023-10-27 | 1 | 1,1,1,2 | x |  |  | 0%
1,1,1,3 | Corrosion protection coating to reinforcing | 2023-10-30 | 2023-11-01 | 2 | 1,1,1,2,1 |  | x |  | 0%
1,1,1,4 | Bonding Layer to existing | 2023-11-01 | 2023-11-03 | 2 | 1,1,1,3 |  | x |  | 0%
1,1,2 | Patch Repair (hand place) | [7 empty] | 0%
1,1,2,1 | Repair <25mm in thickness | 2023-11-06 | 2023-11-06 | 1 | 1,1,1,3 |  | x |  | 0%
1,1,2,2 | Repair <25mm in thickness but <50mm | 2023-11-06 | 2023-11-06 | 1 | 1,1,1,3 |  | x |  | 0%
1,1,3 | Patch Repair (Grout) | [7 empty] | 0%
1,1,3,1 | >50mm | 2023-11-06 | 2023-11-06 | 1 | 1,1,1,3 |  | x |  | 0%
1,1,3,2 | Formwork | 2023-11-06 | 2023-11-06 | 1 | 1,1,1,3 |  | x |  | 0%
1,1,4 | Reinforcement (Provisional) | [7 empty] | 0%
1,1,4,1 | Supply, replace badly corroded reinforcing | 2023-11-06 | 2023-11-10 | 5 | 1,1,3,2 |  | x |  | 0%
1,1,4,2 | Apply skim coat to seal all blow holes and defects in concrete substrate | 2023-11-13 | 2023-11-15 | 2 | 1,1,4,1 |  | x |  | 0%
1,1,4,2,1 | Inspect and Sign off QCP | 2023-11-15 | 2023-11-15 | 1 | 1,1,4,2 | x | x | x | 0%
1,1,5 | Curing | 2023-11-15 | 2023-11-17 | 2 | 1,1,4,2 |  |  |  | 0%
1,1,6 | Testing material & workmanship | 2023-11-17 | 2023-11-22 | 4 | 1,1,5 | x | x |  | 0%
1,1,7 | Sumbit and approve payment certificate | 2023-11-22 | 2023-11-23 | 1 | 1,1,6 | x | x |  | 0%
1,1,8 | Sumbit partial Invoice | 2023-11-23 | 2023-11-28 | 3 | 1,1,6 | x |  |  | 0%
1,1,9 | Approve invopice(s) | 2023-11-28 | 2023-12-01 | 3 | 1,1,8 |  |  | x | 0%
1.2 | Surface preparation (Bare surface) | [7 empty] | 0%
1,2,1 | Remove existing coating to spoil | 2023-12-04 | 2023-12-06 | 2 | 1,1,6 |  | x |  | 0%
1,2,2 | High pressure wash all concrete surfaces using a 350 bar 16litres/min | 2023-12-06 | 2023-12-08 | 2 | 1,2,1 |  | x |  | 0%
1.3 | Coating/ Lining (Bare Concrete) | [7 empty] | 0%
1,3,1 | Apply Polyurea coating as per specification | 2023-12-11 | 2023-12-13 | 2 | 1,2,2 |  | x |  | 0%
1,3,2 | Terminate lining around pipe using Sikaflex 11FCT15 x 15 mm triangular sealent | 2023-12-14 | 2023-12-15 | 1 | 1,2,1 |  | x |  | 0%
1,3,3 | Install motar fillet between wall and floor 30 x 30 mm with ProStrct 528VO | 2023-12-15 | 2023-12-15 | 1 | 1,3,2 |  | x |  | 0%
1,3,4 | 200 x 2 mm Combiflex bandage set in Sikadur 3 CF | 2023-12-15 | 2023-12-15 | 1 | 1,3,3 |  | x |  | 0%
1.4 | Concrete Repair (Lining) | [7 empty] | 0%
1,4,1 | Break out defective concrete to spoil | [7 empty] | 0%
1,4,1,1 | Spall depths not exceeding 25mm | 2024-01-10 | 2024-01-12 | 2 | 0 |  | x |  | 0%
1,4,1,2 | Spall depths not exceeding 25mm and not exceeding 50mm deep | 2024-01-10 | 2024-01-12 | 2 | 0 |  | x |  | 0%
1,4,1,3 | Spall depths exceeding 50mm | 2024-01-10 | 2024-01-12 | 1 | 0 |  | x |  | 0%
1,4,1,4 | Corrosion protection coating to reinforcing | 2024-01-15 | 2024-01-17 | 2 | 1,4,1,1;1,1,2;1,4,1,3 |  | x |  | 0%
1,4,1,5 | Bonding Layer to existing | 2024-01-17 | 2024-01-18 | 1 | 1,4,1,4 |  | x |  | 0%
1,4,2 | Patch Repair (hand place) | [7 empty] | 0%
1,4,2,1 | Repair <25mm in thickness | 2024-01-18 | 2024-01-18 | 1 | 1,4,1,5 |  | x |  | 0%
1,4,2,2 | Repair <25mm in thickness but <50mm | 2024-01-18 | 2024-01-19 | 1 | 1,4,1,5 |  | x |  | 0%
1,4,3 | Patch Repair (Grout) | [7 empty] | 0%
1,4,3,1 | >50mm | 2024-01-19 | 2024-01-19 | 1 | 1,4,1,5;1,4,1,5 |  | x |  | 0%
1,4,3,2 | Formwork | 2024-01-22 | 2024-01-24 | 2 | 1,4,3,1 |  | x |  | 0%
1,4,4 | Reinforcement (Provisional) | [7 empty] | 0%
1,4,4,1 | Supply, replace badly corroded reinforcing | 2024-01-25 | 2024-01-31 | 4 | 1,4,3,2 |  | x |  | 0%
1,4,4,2 | Apply skim coat to seal all blow holes and defects in concrete substrate | 2024-02-01 | 2024-02-05 | 2 | 1,4,4,1 |  | x |  | 0%
1,4,4,2,1 | Inspect and Sign off QCP | 2024-02-05 | 2024-02-05 | 2 | 1,4,4,2 | x | x | x | 0%
1,4,5 | Curing | 2024-02-05 | 2024-02-07 | 2 | 1,4,5 |  |  |  | 0%
1,4,6 | Testing material & workmanship | 2024-02-07 | 2024-02-07 | 1 | 1,4,6 | x | x |  | 0%
1,4,7 | Sumbit payment certificate | 2024-02-08 | 2024-02-08 | 1 | 1,4,6 | x | x |  | 0%
1,4,8 | Sumbit partial Invoice | 2024-02-08 | 2024-02-08 | 1 |  | x |  |  | 0%
1,4,9 | Approve invoice(s) | 2024-02-12 | 2023-02-15 | 3 | 1,4,8 |  |  | x | 0%
1.5 | Surface preparation (Defective concrete) | [7 empty] | 0%
1,5,1 | Remove existing coating to spoil | 2024-02-05 | 2024-02-07 | 2 | 0 |  | x |  | 0%
1,5,2 | High pressure wash all concrete surfaces using a 350 bar 16litres/min | 2024-02-07 | 2024-02-09 | 2 | 1,5,1 |  | x |  | 0%
1.6 | Coating/ Lining (Defective Concrete) | [7 empty] | 0%
1,6,1 | Apply Polyurea coating as per specification | 2024-02-09 | 2024-02-09 | 1 | 1,5,2 |  | x |  | 0%
1,6,2 | Terminate lining around pipe using Sikaflex 11FCT15 x 15 mm triangular sealent | 2024-02-12 | 2024-02-13 | 2 | 1,5,2 |  | x |  | 0%
1,6,3 | Install motar fillet between wall and floor 30 x 30 mm with ProStrct 528VO | 2024-02-13 | 2024-02-16 | 3 | 1,6,2 |  | x |  | 0%
1.7 | Concrete Repair(Unit 066) | [7 empty] | 0%
1,7,1 | Break out defective concrete to spoil | [7 empty] | 0%
1,7,1,1 | Spall depths not exceeding 25mm | 2024-02-16 | 2024-02-19 | 2 | 0 |  | x |  | 0%
1,7,1,2 | Spall depths not exceeding 25mm and not exceeding 50mm deep | 2024-02-16 | 2024-02-19 | 2 | 0 |  | x |  | 0%
1,7,1,3 | Spall depths exceeding 50mm | 2024-02-20 | 2024-02-20 | 1 | 0 |  | x |  | 0%
1,7,1,4 | Corrosion protection coating to reinforcing | 2024-02-20 | 2024-02-22 | 2 | 1,7,1,1;1,7,1,2;1,7,1,3 |  | x |  | 0%
1,7,1,5 | Bonding Layer to existing | 2024-02-22 | 2024-02-26 | 2 | 1,7,1,4 |  | x |  | 0%
1,7,2 | Patch Repair (hand place) | [7 empty] | 0%
1,7,2,1 | Repair <25mm in thickness | 2024-02-26 | 2024-02-26 | 1 | 1,7,1,5 |  | x |  | 0%
1,7,2,2 | Repair <25mm in thickness but <50mm | 2024-02-26 | 2024-02-26 | 1 | 1,7,2,1 |  | x |  | 0%
1,7,3 | Patch Repair (Grout) | [7 empty] | 0%
1,7,3,1 | >50mm | 2024-02-26 | 2024-02-26 | 1 | 1,7,2,2 |  | x |  | 0%
1,7,3,2 | Formwork | 2024-02-26 | 2024-02-28 | 2 | 1,7,3,1 |  | x |  | 0%
1,7,4 | Reinforcement (Provisional) | [7 empty] | 0%
1,7,4,1 | Supply, replace badly corroded reinforcing | 2024-02-28 | 2024-03-01 | 3 | 1,7,3,2 |  | x |  | 0%
1,7,4,2 | Apply skim coat to seal all blow holes and defects in concrete substrate | 2024-03-04 | 2024-03-04 | 1 | 1,7,4,1 |  | x |  | 0%
1,7,5 | Curing | 2024-03-04 | 2024-03-06 | 2 | 1,7,4,2 |  |  |  | 0%
1,7,6 | Testing material & workmanship | 2024-03-06 | 2024-03-11 | 4 | 1,7,5 | x | x |  | 0%
1,7,7 | Sumbit payment certificate | 2024-03-11 | 2024-03-11 | 1 | 1,7,5 | x | x |  | 0%
1,7,8 | Sumbit partial Invoice | 2024-03-11 | 2024-03-13 | 3 | 1,7,6 | x |  |  | 0%
1,7,9 | Approve invopice(s) | 2024-03-13 | 2024-03-18 | 3 | 1,7,7 |  |  |  | 0%
Formulas:
Start date = [End Date, row above]
Start date = [Start date, row above]
End Date = [Start date]
End Date = [End Date, row above]